## WBS_sheet
EV Charger Integration with RB-i.MX6UL
S No | Module | Tasks | Estimation(days) | Status | Remarks
1 | WiFi Integration | Enable the ATWILC3000 kernel driver and copy the required firmware files into /lib/firmware | 0.5 | DONE | Work-around is done for copying the ATWILC3000 linux firmware into rootfs But need to figure out the way to add it into linux-firmware recipe itself.
|  | systemD service file to start wpa supplicant on boot |  | DONE
|  | Basic WiFi Testing |  | DONE
2 | LCD & Touch Integration | Enabling the Kernel drivers for LCD and Touch panel | 0.5 | DONE | Added Linux Device tree support for Display and verfied both display and touch using phytec-qtdemo application
|  | Basic testing (LCD and Touch events) with pre built Qt5 demo application |  | DONE
3 | User Switch on 3 GPIOs | Identify and configure the 3 GPIOs on the SBC expansion connector | 0 | DEFERRED | Switches will be connected to TMS controller. Hence no work at MPU side | 0.1
|  | Verify with command line utilities | 0 | DEFERRED |  | 0.1
4 | D-Bus wrapper Library implementation | Understanding the D-Bus IPC mechanism in linux and command line utilities exposure | 2 | DONE
|  | Create a small test application to send and receive data over D-Bus | 1 | DONE | Written a demo application(emitter and listener) using D-Bus C APIs
|  | Identifying the wrapper functions to be part of the library | 1 | DONE
|  | Design Document preparation | 1.5 | TODO | Need to prepare a document How to use the library
|  | Implementing the library | 3 | DONE
|  | Testing the library with basic emitter and listener applications | 1 | DONE | Written a demo application(emitter and listener) using dbus-wrapper library APIs
5 | CAN Application implementation | Identifying the incoming and outgoing CAN frames and Defining the frame format | 1 | DONE
|  | Design Document preparation (Including JSON string format for D-Bus paylod) | 1.5 | TODO
|  | Implementing CAN bus initialization and operations(read/write) APIs, D-Bus emitter, listener threads and its synchronization Convert JSON string to CAN frame and vice versa | 4 | DONE
|  | Testing and Re-work | 1 | DONE
6 | Switch selection Application | Design Document preparation (Including JSON string format for D-Bus paylod) | 0 | DEFERRED | Switches will be connected to TMS controller. Hence no work at MPU side | 1
|  | Implementation of GPIOD library based GPIO handling for 3 GPIOS, D-Bus emitter, listener threads and its synchronization, Should emit the D-Bus signal if and only if there is a state change in the GPIO. Default STATE = LOW | 0 | DEFERRED |  | 2.5
|  | Testing and Rework | 0 | DEFERRED |  | 1
7 | AWS MQTT Application | Understanding AWS embedded C SDK MQTT APIs and JSON parser | 1.5 | TODO
|  | Define the JSON string format for subscribing and publishing message payload | 1
|  | Design Document prepation | 1
|  | Implementing PubSub model, D-Bus emitter, listerner thread creation and synchronization, MQTT connection/disconnection hanling Update the LCD in accordance with Cloud and charging station parameters | 6
|  | Testing and Rework | 1
8 | Smart charger application | Identifying the incoming and outgoing D-bus signals and their payloads | 1.5 | TODO
|  | Design Document preparation | 3 | TODO
|  | Implementation | 7 | TODO
|  | Integration Testing and Rework with other modules(CAN application, AWS MQTT Application, Switch selection Application and LCD Application) | 2 | TODO
9 | LCD Application | Identifying the different buttons, check boxes etc to be displayed on LCD |  | TODO
Identifying the paraments to be shown on LCD
identifying and Defining the LCD Display each screen layout blueprint
Defining the JSON string format for incoming and outgoing D-Bus signal payloads
Design Document preparation
GUI application implementation
Integration Testing and Rework with other modules(CAN application, AWS MQTT Application, Switch selection Application and Smart charger Application)
10 | Yocto layer management | Download the i.MX6UL Yocto source | 1 | DONE
|  | Add RB-i.MX6UL device tree and kernel configs | 1 | DONE
|  | Create a meta layer for iisc and have all the IISC related development under this layer | 1 | DONE
|  | Create a custom Yocto build image for the project | 1
11 | System level testing and Re-work | Test with Web Application, Mobile Application, LCD and Selection Switches simultaneously | 5 | TODO
|  | Total Man days | 51
| Note | The above timelines are without OCPP considerations
| Open point | To display Date and Time on LCD, need RTC module.
| Start Date | 26th September 2022
| Expected End Date | 5th December 2022
dbus-listener - 2.7KB memory and 12% CPU
dbus-emitter - 4KB memory and 15% CPU

## HW_Componets
EV Charger Integration with RB-i.MX6UL Hardware Components list
S No | Hardware Module | part/serial Number | Quantity | Remarks
1 | RB-i.MX6UL SBC Board | RB-iMX6UL-1P3 | 1
2 | WiFi Module | ATWILC3000 | 1
3 | 7 Inch LCD with Touch panel | LCD: TM2306DA070L-01 | 1
4 | PCAN Debug cable | PCAN | 1 | This is useful to verify CAN application
5 | RTC Module (TBD) |  | 1